| RISK LOG |  |  |  | PROJECT NAME: |  |  |  |  |  |  |  |  |  |  | PROJECT ID |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  | PROJECT MANAGER: |  |  |  |  |  |  |  |  |  |  | DATE LAST AMENDED |  |  |  |  |
| KEY: | Category - |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | 'E/F' Economic/Financial'; 'E' Environmental; 'L' Legal/Regulatory; 'O/M' Organisational/management; 'P' Political; 'S/C' Strategic/Commercial; 'T/O' Technical/Operational |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Likelihood - 6 = Almost certain, 5 = Likely, 4 = Probable, 3 = Possible, 2 = Unlikely, 1 = Almost impossible Impact: 4 = Catastrophic, 3 = Critical, 2 = Significant, 1 = Marginal |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Priority Score - Purple (18-24: Catastrophic Risk); Red (10-16: Critical Risk); Amber (9-8: Significant Risk); Green (1-6: Marginal Risk) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  | Residual |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  | Likelihood | Impact | Priority | Date |  | Likelihood |  | Impact | Priority | Owner / |  |  | Date of |  | Related |
| ID | Type |  | Category | Description |  |  |  |  | Countermeasure or response |  |  |  |  |  |  | Notes | last | Status |  |
|  |  |  |  |  |  |  |  | identified |  |  |  |  |  | Actioner |  |  |  |  | RAID ID |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | update |  |  |
|  |  |  |  | Lack of regional governance structure impacts collaboration |  |  |  |  | Inter Authority Agreement (IAA) in place to cover terms of the |  |  |  |  |  |  |  |  |  |  |
| R01 | Risk |  | L | between local authorities | 5 | 3 | 15 | 27/10/17 | co-operation | 4 |  | 2 | 8 | Sam Bryan |  |  |  |  |  |
|  |  |  |  | Non-delivery risk between multiple partners- leverage factor is |  |  |  |  | Inter Authority Agreement (IAA) in place to cover terms of the |  |  |  |  |  |  |  |  |  |  |
| R02 | Risk |  | O/M |  | 4 | 4 | 16 | 27/10/17 | co-operation. Risk will be bourne at local level | 3 |  | 3 | 9 | Sam Bryan |  |  |  |  |  |
|  |  |  |  | not met |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  | Financial procedures in place will limit grant spend to |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  | High level political commitment sort for submissions of bid/ |  |  |  |  |  |  |  |  |  |  |
| R03 | Risk |  | P |  | 3 | 3 | 9 | 27/10/17 | Regular communications and updates on progress/ Inclusive | 3 |  | 2 | 6 | Sam Bryan |  |  |  |  |  |
|  |  |  |  | Lack of political support hinders investment programme |  |  |  |  | steering committee structure |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  | Inter Authority Agreement (IAA) in place to cover terms of the |  |  |  |  |  |  |  |  |  |  |
| R04 | Risk |  | O/M | Bristol does not meet leverage factor | 4 | 4 | 16 | 27/10/17 | co-operation. Risk will be bourne at local level | 3 |  | 3 | 9 | Sam Bryan |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  | Financial procedures in place will limit grant spend to |  |  |  |  |  |  |  |  |  |  |
| R05 | Risk |  | O/M | Prioritisation of programmes skews regional balance of the | 3 | 3 | 9 | 27/10/17 | Prioritisation of programmes will be agreed within steering | 2 |  | 6 | 12 | Sam Bryan |  |  |  |  |  |
|  |  |  |  | programme |  |  |  |  | groups and the steering committee |  |  |  |  |  |  |  |  |  |  |
| R06 | Risk |  | E/F | Delivery Unit is unable to secure sufficient capital or low enough co | 3 | 3 | 9 | 27/10/17 | Majority of projects have capital secured | 2 |  | 3 | 6 | Sam Bryan |  |  |  |  |  |
| R07 | Risk |  | E/F | Political changes in subsidy support alter viability of investment | 4 | 4 | 9 | 27/10/17 | Diversity of programme means that the investment portfolio | 2 |  | 3 | 6 | Sam Bryan |  |  |  |  |  |
|  |  |  |  | programme |  |  |  |  | is not exposed to anyone particular subsidy regime |  |  |  |  |  |  |  |  |  |  |
| R08 | Risk |  | p | Wider political changes such as the Uk leaving the EU impact the | 3 | 2 | 6 | 27/10/17 | Confirm with EIB | 2 |  | 2 | 4 | Sam Bryan | Call with EIB Oct 2017 |  | 27/10/17 | Closed |  |
|  |  |  |  | EIB technical assistance programme |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  | This risk is specific to the delivery of projects and investment |  |  |  |  | Prioritisation will ensure that only those biomass and district |  |  |  |  |  |  |  |  |  |  |
| R09 | Risk |  |  | within the timescales of the ELENA Programme. | 4 | 4 | 16 | 27/10/17 | heating schemes that will count towards the leverage target | 3 |  | 3 | 9 | Sam Bryan |  |  |  |  |  |
|  |  |  |  | There is a risk that the proposed district heating projects will |  |  |  |  | are progressed in the short term. |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  | Lack of procurement resource to support programme delivery |  |  |  |  | Dedicated procurement support will be sought under the |  |  |  |  |  |  |  |  |  |  |
| R10 | Risk |  |  | The ELENA Programme is bringing forward a broad range of | 4 | 4 | 16 | 27/10/17 |  | 3 |  | 2 | 6 | Sam Bryan |  |  |  |  |  |
|  |  |  |  | projects within a relatively short period of time, all of which |  |  |  |  | Technical Assistance programme. |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  | Inability to access appropriate legal and financial resource and |  |  |  |  | Dedicated financial and legal support will be sought under |  |  |  |  |  |  |  |  |  |  |
| R11 |  |  |  | advice | 4 | 4 | 16 | 27/10/17 | the Technical Assistance programme as a centralised | 3 |  | 2 | 6 | Sam Bryan |  |  |  |  |  |
|  |  |  |  | The projects being brought forward by the ELENA Programme |  |  |  |  | resource |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  | 0 |  |  |  |  |  | 0 |  |  |  |  |  |  |
|  |  |  |  |  |  |  | 0 |  |  |  |  |  | 0 |  |  |  |  |  |  |
|  |  |  |  |  |  |  | 0 |  |  |  |  |  | 0 |  |  |  |  |  |  |
|  |  |  |  |  |  |  | 0 |  |  |  |  |  | 0 |  |  |  |  |  |  |
|  |  |  |  |  |  |  | 0 |  |  |  |  |  | 0 |  |  |  |  |  |  |

ASSUMPTION LOG

PROJECT NAME:

PROJECT MANAGER:

PROJECT ID

DATE LAST AMENDED

Priority Score ( IMPACT if assumption correct ) :- High (Major/ Catastropic)	Medium (Moderate/ High)	Low (Low/ Moderate)

ID

Assumption

Type

Date raised

Assumption description

(including source)

Confidence

level %

Further work required to increase confidence

Associated impact

Priority

Owner

Date of last

update

Status

BC line

number

(If applicable)

Product ID

(If applicable)

Related

RAID ID

| ISSUE |  | PROJECT NAME: |  |  |  |  |  |  |  | PROJECT ID: |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| LOG |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | PROJECT MANAGER: |  |  |  |  |  |  |  | DATE LAST AMENDED: |  |  |  |  |  |  |  |  |  |
| KEY: |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Category: C = Concern; OS = Off specification; |  | Q = Question/Query; RFC = Request for change |  | Status: | O = Open; CL = Closed; |  |  | E = Escalated |  |  |  |  |  |  |  |  |  |  |
|  | Priority Score - Red (Major/ Catastrophic Impact); Amber (Moderate/ High Impact); Green (Low Impact) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Date |  |  |  |  |
| ID | Category | Description |  | Impact or potential impact |  |  | Priority |  | Action / Decision | Raised by |  | Owner | Actioner |  |  |  | Status | Exception | Related |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  | Raised |  | Resolved |  | (Y/N) | RAID ID |

| DEPENDENCY |  |  | PROJECT NAME: |  |  |  |  |  |  |  |  | PROJECT ID: |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| LOG |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  | PROJECT MANAGER: |  |  |  |  |  |  |  |  | DATE LAST AMENDED: |  |  |  |  |  |
|  |  |  | Priority Score ( IMPACT if delays in delivery) :- High (Mission Critical) Medium (Major) |  |  |  |  | Low (Minor) |  |  |  |  |  |  |  |  |  |
|  | Management information |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  | Provider (Giver) Workpackage | Dependent (Receiver) |  |  | Date |  | Associated impact if dependency not |  |  |  | Dependency | Date of last |  |
| ID | Date Raised | Level | Internal / | Category | / Workstream / Project / | Workpackage / Workstream / |  | Description of dependency |  | Date f'cast |  | Priority |  | Actions / Decisions |  |  | Status |
|  |  | (Port / Prog / Proj) | External |  | Programme | Project / Programme |  |  | required |  | met |  |  |  | Owner | update |  |

| Change Log | Project Name: |  |  | Project ID: |  | Project Manager: |  |  | Date last |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  |  |  |  |  | amended: |  |  |  |
| Project Tolerances: | Time |  | Benefits |  | Cost |  |  |  |  |  |  |  |
|  | Scope |  | Risk |  | Quality |  |  |  |  |  |  |  |

Impact RAG Score:- Red (Major/ Catastrophic Impact); Red/Amber (Moderate/ High Impact); Green (Low Impact)

Impact assessment

Source or change

Is the change outside agreed

tolerances?

ID	Date Raised

Prog/ Proj / Workpackage / Individual

Change type

Description

Time

Benefit

Cost

Scope

Risk

Quality

Internal impact

External impact

Escalation

req'd?

RAG

Actions / Decisions

Date for	Date of Last

Review	Update

Status

Related

RAID ID

Do not delete this sheet - the information on this page is used to populate the drop down menues on the log templates

| Risk type | Risk category | Likelihood/Impact | R Status | Assumtion type | Priority | A Status | % | I category | I priority | I status Escalation |  | D category D type |  | D level | D status | D priority | Delivery status | C type | C tolerance breach | C RAG | C Status |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Opportunity | E | 1 | Open | Benefit | High | Open | 0% | C | Red | Open | Y | Constraint | INTERNAL | Portfolio | Open | High | On target | Concern | Y | Red | Approved |
| Risk | E/F | 2 | Closed | Cost | Medium | Closed | 25% | OS | Amber | Closed | N | Hard | EXTERNAL | Programme | Closed | Medium | At risk | Off specification | N | Amber | Pending |
|  | L | 3 | Escalated | Delivery/Plan | Low |  | 50% | Q | Green | oncession |  | Soft |  | Project |  | Low | Critical issue | Question/Query |  | Green | Rejected |
|  | O/M | 4 |  | Resource |  |  | 75% | RFC |  | Escalated |  | TBD |  |  |  |  |  | Request for change |  |  | Escalated - Approved |
|  | P | 5 |  |  |  |  | 90% |  |  |  |  |  |  |  |  |  |  |  |  |  | Escalated - Pending |
|  | S/C | 6 |  |  |  |  | 100% |  |  |  |  |  |  |  |  |  |  |  |  |  | Escalated - Rejected |
|  | T/O |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |