## Instructions
Project Status Report Template
2015 Version (v1.02)
Published by Axia Consulting Ltd, 17 New Road Avenue, Chatham, Kent ME4 6BA, United Kingdom.
Web: www.axia-consulting.co.uk Email: info@axia-consulting.co.uk
Axia Consulting Ltd gives no warranty (either expressed or implied) in relation to the quality, accuracy, performance and fitness for purpose of this 'Project Status Report Template'. Axia Consulting Ltd will not be liable for any loss or damage (whether directly or indirectly suffered), or any consequential loss arising from the use of this 'Project Status Report Template'.
Copyright © 2015 Axia Consulting Ltd. All rights reserved.
This ‘Project Status Report Template’ is free for personal use and to help you with projects internally within your organisation. However, you are not permitted to display this ‘Project Status Report Template’ on the Internet, whether in part or whole, whether modified or not, nor to advertise, resell or obtain a commercial benefit from it
Sample 'accounting software selection' project data has been included for illustration purposes.
INSTRUCTIONS are below (click the tab at the bottom of the screen to access the Project Status Report Template)
1. Delete the sample data.
2. Add your specific details as required. The columns are:
A - Ref No - allocate a unique number
B - Tasks and deliverables
C - Plan start date
D - Plan end date
E - Actual start date
F - Actual end date
G - Completion Status - click cell to choose status
H - Owner responsible for task
I - Assigned to
J - Notes
If you wish amend the 'status terms' the instructions are:
1. Amend your ‘status terms' in cells F67-F70 – or extend the range for more terms.
2. Click cell G6 (or any other ‘Status’ cell)
3. Then select the ‘Data’ tab - then in Data Tools, select ’Data Validation’- then Settings and check that the Source is: =$F$67:$F$70 - or whatever the range is for your different statuses. Then click ‘OK’
4. Then click cell G6 scroll tab to test out your different status options.
5. If they are correct, then copy and paste to the other ‘status’ cells.
If you wish to amend the Red/Amber/Green status colours, the instructions are:
1. Click / highlight cells
2. In the 'Home' tab, select Styles, then Conditional Formating - then select 'Highlight Cells Rules, then select 'Equal To' and amend the conditions and colours.
The worksheet is completely flexible. Rows and columns may be resized. Data may be amended. Additional worksheets may be added.
Further information about software selection may be found at:
http://www.axia-consulting.co.uk/html/resources.html

## Project Status Report Template
Project Status Report Template for:
Sample accounting software selection data included for illustration
| Date: 1 July 2015 | Report: 5
Ref | Task / Deliverable | Plan Start Date | Plan End Date | Actual Start Date | Actual End Date | Status | Owner | Assigned to | Notes
1 | Requirements specification
1.1 | User interviews / use Axia Template | 2015-06-01 | 2015-06-11 | 2015-06-01 | 2015-06-11 | Completed | M | U, IT
1.2 | Consolidate requirements | 2015-06-10 | 2015-06-12 | 2015-06-10 | 2015-06-12 | Completed | M | U, IT
1.3 | 1st draft of requirements | 2015-06-12 | 2015-06-12 | 2015-06-12 | 2015-06-15 | Completed | M | U
1.4 | Review and amend requirements | 2015-06-15 | 2015-06-16 | 2015-06-16 | 2015-06-18 | Completed | M | U
1.5 | Sign off requirements | 2015-06-17 | 2015-06-17 | 2015-06-19 | 2015-06-19 | Completed | PS | M, PS
2 | RFI (Request for Information)
2.1 | Identify potential systems, vendors | 2015-06-15 | 2015-06-16 | 2015-06-16 | 2015-06-18 | Completed | PM | IT, U
2.2 | Prepare RFI | 2015-06-16 | 2015-06-18 | 2015-06-17 | 2015-06-19 | Completed | PM | IT, U
2.3 | Contact vendors / issue RFI | 2015-06-19 | 2015-06-19 | 2015-06-22 | 2015-06-22 | Completed | PM | IT
3 | Short list systems, vendors
3.1 | Review and analyse RFI results | 2015-06-25 | 2015-06-29 | 2015-06-29 |  | In Progress | PM | IT, U
3.2 | Compare against requirements | 2015-06-26 | 2015-06-30 | 2015-06-30 |  | In Progress | PM | IT, U
3.3 | Identify short list of 3 or 4 vendors | 2015-07-01 | 2015-07-01 |  |  | Delayed | PM | IT, U
3.4 | Inform vendors of status | 2015-07-01 | 2015-07-01 |  |  | Delayed | PM | IT
4 | Systems demonstrations
4.1 | Arrange with short listed vendors | 2015-07-01 | 2015-07-01 |  |  | Not Started | PM | IT
4.2 | Create demo scripts / questions | 2015-06-22 | 2015-06-24 |  |  | Not Started | PM | U, IT
4.3 | Attend demonstrations | 2015-07-06 | 2015-07-07 |  |  | Not Started | PM | U, IT
4.4 | Review findings | 2015-07-08 | 2015-07-08 |  |  | Not Started | PM | U, IT
4.5 | Reduce short list to 2 or 3 vendors | 2015-07-08 | 2015-07-08 |  |  | Not Started | PM | U, IT
5 | Refine new system design thoughts
5.1 | Additional design thoughts | 2015-07-01 | 2015-07-02 |  |  | Not Started | PM, M | U, IT
5.2 | Details from systems demonstrated | 2015-07-06 | 2015-07-08 |  |  | Not Started | PM, M | U, IT
5.3 | Revise system design | 2015-07-09 | 2015-07-09 |  |  | Not Started | PM, M | U, IT
6 | RFP (Request for proposal)
6.1 | Prepare RFP | 2015-06-25 | 2015-07-01 |  |  | Not Started | PM | IT, U
6.2 | Issue to short listed vendors | 2015-07-13 | 2015-07-13 |  |  | Not Started | PM | IT
6.3 | Review, analyse, score responses | 2015-07-20 | 2015-07-22 |  |  | Not Started | PM | IT, U
7 | Further investigations
7.1 | Prototyping | 2015-07-23 | 2015-08-05 |  |  | Not Started | PM | IT, U
7.2 | Test system | 2015-07-27 | 2015-07-30 |  |  | Not Started | PM | IT, U
7.3 | Queries from RFP responses | 2015-07-30 | 2015-08-03 |  |  | Not Started | PM | IT, U
7.4 | Hardware, network, database | 2015-08-04 | 2015-08-06 |  |  | Not Started | PM | IT
8 | Detailed system demonstrations, vendor discussions
8.1 | Cover all points from 6, 7 above | 2015-08-10 | 2015-08-14 |  |  | Not Started | PM | U, IT
8.2 | Resolve outstanding queries, issues | 2015-08-10 | 2015-08-14 |  |  | Not Started | PM, M | U, IT
9 | Reference site visits
9.1 | Identify who to visit | 2015-08-11 | 2015-08-11 |  |  | Not Started | M | U, IT
9.2 | Determine agenda | 2015-08-11 | 2015-08-12 |  |  | Not Started | M, PM | U, IT
9.3 | Arrange visits | 2015-08-12 | 2015-08-12 |  |  | Not Started | M | U
9.4 | Attend visits | 2015-08-17 | 2015-08-18 |  |  | Not Started | M, PM | U, IT
9.5 | Contact other sites by phone | 2015-08-13 | 2015-08-13 |  |  | Not Started | M | U
10 | Decision
10.1 | Pull all results & findings together | 2015-08-19 | 2015-08-21 |  |  | Not Started | PS | PM, M, IT,U
10.2 | Prepare proposal paper | 2015-08-24 | 2015-08-25 |  |  | Not Started | PS | PM, M
10.3 | Board / steering group meeting | 2015-09-03 | 2015-09-03 |  |  | Not Started | B | B, SG, PS
10.4 | Decision made | 2015-09-03 | 2015-09-03 |  |  | Not Started | B | B, SG, PS
10.5 | Inform vendors | 2015-09-03 | 2015-09-03 |  |  | Not Started | PS | PM
10.6 | Final contract, SLA negotiation | 2015-09-04 | 2015-09-04 |  |  | Not Started | PS | P, PM
11 | Project management
11.1 | Project plan | 2015-06-01 | 2015-06-01 |  |  | Completed | PS | PM
11.2 | Project kick-off meeting | 2015-06-01 | 2015-06-01 |  |  | Completed | PS | PM, ALL
11.3 | Weekly progress meetings | 2015-06-01 | 2015-09-04 |  |  | In Progress | PS | PM, U, IT
[5 empty] | Key to Status |  |  | Key to Owner / Assigned
[5 empty] | Not Started |  |  | PS = project sponsor
[5 empty] | In Progress |  |  | PM = project manager
[5 empty] | Delayed |  |  | IT = IT staff
[5 empty] | Completed |  |  | U = users
M = manager (user)
P = procurement
B = board
SG = steering group