## High Level Project Plan
HIGH LEVEL PROJECT PLAN
| EQUIPMENT PROCUREMENT |  |  |  | RESOURCE ALLOCATION |  |  |  | SITE PREP & SAFETY CHECK
| W1 | - | W6 | Mar 3 - Apr 11, 2025 | W1 | - | W3 | Mar 3 - Mar 21, 2025 | W1 | - | W4 | Mar 3 - Mar 28, 2025
| Marketing team (Adam Walker) |  |  |  | Project Management Team (John Smith) |  |  |  | Safety and Compliance Team (Jane Doe)
| 1 |  | Source, order, and procure all necessary equipment. Coordinate delivery schedules and verify that all equipment meets required specifications. |  | 2 |  | Define the project scope, allocate necessary resources, and set timelines. Identify stakeholders and set up initial meetings for project kick-off. |  | 3 |  | Conduct site inspections, ensure compliance with all safety regulations, and prepare the site for installation of new manufacturing equipment.
| INSTALL MANUFACTURING LINE |  |  |  | SYSTEM INTEGRATION |  |  |  | STAFF TRAINING
| W7 | - | W11 | Apr 14 - May 23, 2025 | W12 | - | W16 | May 26 - Jun 27, 2025 | W14 | - | W16 | Jun 9 - Jun 27, 2025
| Engineering Team (Emily White) |  |  |  | IT and Automation Team (David Green) |  |  |  | Training Team (Sarah Blue)
| 4 |  | Install the new manufacturing line equipment, ensure correct setup, and conduct initial testing to confirm functionality and performance. Perform SAT. |  | 5 |  | Integrate new equipment with existing systems, perform software updates, and conduct comprehensive testing to ensure seamless operation. |  | 6 |  | Train staff on operating new equipment, ensure certification, and provide ongoing support to address any operational questions or concerns.
| QUALITY ASSURANCE |  |  |  | PILOT PRODUCTION RUN |  |  |  | FULL PRODUCTION LAUNCH
| W17 | - | W18 | Jun 30 - Jul 11, 2025 | W19 | - | W20 | Jul 14 - Jul 25, 2025 | W21 | - | W22 | Jul 28 - Aug 8, 2025
| Quality Control Team (Robert Black) |  |  |  | Production Team (Laura Red) |  |  |  | Operations Team (James Yellow)
| 7 |  | Implement quality control measures, conduct thorough inspections, and ensure all processes comply with industry standards and regulations. |  | 8 |  | Conduct a pilot production run, closely monitor performance, and make necessary adjustments to optimize the manufacturing process. |  | 9 |  | Launch full production, closely monitor output, and ensure smooth operation of the new manufacturing line to meet production targets. Technologists to write reports.